## Sheet1
Project Name: | Development of the ASEAN Guideline on the Verification of Weigh-in-Motion Instruments
Task Code
Task Name
Country Office: | Cambodia
Activity | Activity Name | Total Cost | Remarks
AUD
1 | Developing detailed project workplan |  | Professional fees for consultant to organise a kick-off meeting and develop and finalise a detailed project workplan.
2 | Drafting Guideline Outline and Conducting Stakeholder Consultations |  | Professional fees for consultant to develop and finalise the Guideline outline, conduct stakeholder consultations, and produce a stakeholder consultation report
3 | Drafting ASEAN Guideline on Verification of WIM Instruments |  | Professional fees for a consultant to develop the ASEAN Guideline on the verification of WIM instruments, prepare and deliver an online regional validation workshop, produce a validation workshop report, finalise the Guideline based on comments from all relevant stakeholders, and lay out the design of the final Guideline.
4.1 | Technical preparation and delivery of online regional training workshop and in-country training workshops in three AMS (TBC) |  | Professional fees for consultant to prepare and deliver the online and in-country training workshops, produce post-workshop reports, and develop high-level Guideline implementation plans for the selected AMS.
5 | Developing project reports |  | Professional fees for consultant to develop and finalise a progress report and a project completion report, and draft a six-month post-project survey questionnaire
6 | Professional fee for the WIM expert (to be jointly recruited by RT4D and the consultant) | 30000 | Maximum up to AUD 30,000
7 | Contigency (3%) |  | Utilised based on RT4D Project Manager's Approval
TOTAL (AUD) |  | 30000

## Act.Bud.rev
Project Name | Development of the ASEAN Guideline on the Verification of Weigh-in-Motion Instruments
Task Code
Task Name
Country Office
Project Manager
Budget Approved Date
Activity | Activity Name | Category | Unit | Quantity | Currency | Rate/unit | Currency | Total Cost | Remarks
AUD Per Activity
1 | Developing detailed project workplan | [6 empty] | 0
1.1.1 | A team of consultants to organise a kick-off meeting and develop and finalise a detailed project workplan (excluding the professional fee for WIM expert) | Professional Services | Day | 3 | AUD |  | AUD | 0
2 | Drafting Guideline Outline and Conducting Stakeholder Consultations | [6 empty] | 0
2.1.1 | A team of consultants to develop and finalise the Guideline outline, conduct stakeholder consultations, and produce a stakeholder consultation report (excluding the professional fee for WIM expert) | Professional Services | Day | 9 | AUD |  | AUD | 0
3 | Drafting ASEAN Guideline on Verification of WIM Instruments | [6 empty] | 0
3.1.1 | A team of consultants to develop the ASEAN Guideline on the verification of WIM instruments, prepare and deliver an online regional validation workshop, produce validation workshop report, and finalise the Guideline based on comments from all relevant stakeholders. (excluding the professional fee for WIM expert) | Professional Services | Day | 15 | AUD |  | AUD | 0
3.1.2 | Professional fees to layout design the final Guideline | Professional Services | Lumpsum | 1 | AUD |  | AUD | 0
4 | Technical delivery of online regional and in-country training workshops | [6 empty] | 0
4.1.1 | A team of consultants to develop assessment criteria for AMS nomination and support the selection of AMS. (excluding the professional fee for WIM expert) |  | Day | 1 | AUD |  | AUD | 0
4.1.2 | A team of consultants to prepare and deliver online training workshops on the Guidelines, produce workshop materials and post-workshop report. (excluding the professional fee for WIM expert) | Professional Services | Day | 4 | AUD |  | AUD | 0
4.1.3 | In-person training workshop 1: A team of consultants to prepare and deliver in-person training workshops on the Guidelines, produce workshop materials and post-workshop report, and develop a high-level implementation plan for the trained AMS. (excluding the professional fee for WIM expert) |  | Day | 6 | AUD |  | AUD |  | Note for bidders: - Payment for Workshop 1 is subject to the approval of a request from AMS. The consultant will be authorised to begin work once the relevant Expression of Interest is approved. - RT4D will cover travel-related costs for up to 3 consultants to deliver this in-person workshop. The bidder thus does not need to budget for the travel costs in this financial proposal.
4.1.4 | In-person training workshop 2: A team of consultants to prepare and deliver in-person training workshops on the Guidelines, produce workshop materials and post-workshop report, and develop a high-level implementation plan for the trained AMS. (excluding the professional fee for WIM expert) | Professional Services | Day | 6 | AUD |  | AUD |  | Note for bidders: - Payment for Workshop 2 is subject to the approval of a request from AMS. The consultant will be authorised to begin work once the relevant Expression of Interest is approved. - RT4D will cover travel-related costs for up to 3 consultants to deliver this in-person workshop. The bidder thus does not need to budget for the travel costs in this financial proposal.
4.1.5 | In-person training workshop 3: A team of consultants to prepare and deliver in-person training workshops on the Guidelines, produce workshop materials and post-workshop report, and develop a high-level implementation plan for the trained AMS. (excluding the professional fee for WIM expert) | Professional Services | Day | 6 | AUD |  | AUD |  | Note for bidders: - Payment for Workshop 3 is subject to the approval of a request from AMS. The consultant will be authorised to begin work once the relevant Expression of Interest is approved. - RT4D will cover travel-related costs for up to 3 consultants to deliver this in-person workshop. The bidder thus does not need to budget for the travel costs in this financial proposal.
5 | Developing project reports | [6 empty] | 30000
5.1.2 | Developing and finalising project progress report (long and short versions) (excluding the professional fee for WIM expert) | Professional Services | Day | 4 | AUD |  | AUD | 0
5.1.3 | Developing and finalising project completion report (long and short versions) (excluding the professional fee for WIM expert) | Professional Services | Day | 4 | AUD |  | AUD | 0
5.1.4 | Developing a six-month post-project survey questionnaire (excluding the professional fee for WIM expert) | Professional Services | Day | 2 | AUD |  | AUD | 0
6 | Professional fee for the WIM expert (to be recruited jointly by RT4D and the consultant) | Professional Services | Lumpsum |  | AUD |  | AUD | 30000 | Note for bidder: This line is for covering all professional fees for the WIM expert to implement the project. The RT4D Facility will work with the selected Consultant to jointly identify and select a WIM technical expert. The bidders are welcome to recommend a suitable WIM expert; however, bidders are not required to have an identified WIM expert at the time of proposal submission. The selected Consultant will contract and manage the selected WIM expert. Notwithstanding this arrangement, the RT4D Facility will work closely with the selected Consultant to agree on the scope of inputs, level of effort, and associated fees for the WIM expert, ensuring they are reasonable, market-based, and represent value for money.
7 | Contingency (3%) |  |  |  | AUD |  | AUD |  | Utilised based on RT4D Project Manager's Approval
| Total estimated budget (round-up) |  |  |  | AUD |  |  | 30000
60

## 4.2. Event 1 (hidden)
Activity Name | #REF!
Task Code
Task Name
Country Office | Indonesia
Activity Code | Activity Name | Category | Unit | Quantity | Times | Currency | Rate/unit | Currency | Total Cost | Total Cost | Total | Budget Allocation (AUD) |  | Remarks
[10 empty] | AUD | Per Activity | FY 25-26 | FY 26-27
4.2 | Workshop #1
4.2.1 | Professional fee | [9 empty] | 2752.7145
4.2.1.1 | Professional fee | Professional Services | Day | 2 | 2 | USD | 400 | USD | 1600 | 2446.8573
4.2.1.2 | Transport Consultant | Airfare | Return | 2 | 1 | USD | 100 | USD | 200 | 305.8572
4.2.2 | Participant-related expenses | [6 empty] | 0 |  |  | 5927.8012 |  |  | The way we categorize it at the moment is not clear, this is my suggestion
4.2.2.1 | Local Participant Perdiem | Local Per Diem | Person | 10 | 2 | USD | 10 | USD | 200 | 305.8572
4.2.2.2 | International Participant Perdiem | Overseas Per Diem | Person | 2 | 5 | USD | 170 | USD | 1700 | 2599.7859
4.2.2.3 | Hotel Accommodation | Accommodation | Person | 2 | 4 | USD | 170 | USD | 1360 | 2079.8287
4.2.2.4 | Local Transportation Allowance | Local Transportation | [5 empty] | 0 | 0
4.2.2.5 | Airfare - Consultants | Airfare | [5 empty] | 0 | 0 |  |  |  |  | This repeats line 12
4.2.2.6 | Airfare - RT4D / ASEC | Airfare | [5 empty] | 0 | 0
4.2.2.7 | Airfare - Domestic | Airfare | Return | 2 | 1 | IDR | 5000000 | IDR | 10000000 | 942.3294
4.2.3 | Meeting packages (F&B and hotel venue) | Meetings & Conferences | Lumpsum | 100 | 2 | IDR | 750000 | IDR | 150000000 | 14134.9416 | 14134.9416
4.2.3.1 | Food and beverages | Meetings & Conferences
4.2.3.2 | Hotel venue | Meetings & Conferences
4.2.4 | Event logistics, equipments and HR support | Meetings & Conferences | [5 empty] | 0 | 0 |  | 0
4.2.4.1 | Technical equipment (Backdrop, screen, sound system, mic, phone, simutaneous intepretation cabin, internet for hybrid, etc) | Meetings & Conferences
4.2.4.2 | HR support (reception, liaison, coordination, technical support, etc) | Meetings & Conferences
4.2.4.3 | Event Support - Photography and videos | Meetings & Conferences
4.2.4.4 | RT4D Branding and Stationaries | Meetings & Conferences | [5 empty] | 0 | 0
4.2.5 | Site Visit | Meetings & Conferences | [5 empty] | 0 | 0
4.2.5.1 | Site Visit - Car Rent
4.2.5.2 | Site Visit - Equipment | Meetings & Conferences | [5 empty] | 0 | 0
4.2.5.3 | Site Visit - Refreshment | Meetings & Conferences | [5 empty] | 0 | 0
4.2.6 | Contigency | Meetings & Conferences | [5 empty] | 0 | 0
4.2.7 | Event Management Cost | Subcontractor-External | [5 empty] | 0 | 0
Note on N10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is total sub amount of 4.2.1.x
Note on N13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is total amount of 4.2.2.x
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can we split this cost item into two? Usually, we have local transportation allowances for provincial travel. Then, we need to have another local transportation allowance from their hotel to the venue. Reply: Yes, just copy the row
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This repeats line 12
Note on N21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is total amount of 4.2.2.x
Note on N24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is total amount of 4.2.2.x
Note on C27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I would like to add this one more cost item. The cost could be varied whether you do the video recording or not, so you can split into two lines too in case some events do not do the video. Reply: thank you
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Like Iko’s comment on the summary sheet, I prefer to contingency for the whole project, rather than activity-specific. Reply: noted
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The list is quite comprehensive, but do we still have freedom to add any unforseen cost items after this one? Reply: yes, you can add as many rows as needed

## Participants Cost (hidden)
Country | DSA (USD/day) | Room % of DSA | Lodging Portion (USD) per Day | Overseas Per Diem | Local Per diem* | Notes for Local Per diem | Local Transportation/way* | Notes for Local Transportation
Vietnam | 240 | 55% | 132 | 108 | 34 | Covers local travel, minor refreshments, and incidental expenses | 12 | Common practice for urban areas (e.g., Hanoi/Ho Chi Minh)
Cambodia | 340 | 50% | 170 | 170 | 10 | Same as above; often used by NGOs and donor programs | 10 | NGO standard; sufficient for tuk-tuk or Grab use
Laos | 300 | 60% | 180 | 120 | 10 | Aligned with practice of reducing DSA when meals are covered | 10 | Common NGO standard
Kuala Lumpur | 283 | 71% | 200.93 | 82.07 | 12 | Higher incidental costs; transport via Grab/rail | 10 | Based on Grab/public transport cost per day
Siem Reap | 333 | 68% | 226.44 | 106.56 | 10 | Similar to Phnom Penh standards | 10 | Similar to Phnom Penh; tuk-tuk or small taxi travel
Bangkok* | 300 | 60% | 180 | 120 | 12 | Urban cost + BTS/MRT or taxi allowance | 12 | BTS/MRT + short taxi rides (urban average)
Manila* | 350 | 55% | 192.5 | 157.5 | 12 | Considered reasonable in NGO/multilateral program budgeting | 12 | Jeepney, GrabCar, MRT costs considered
Indonesia | 212 | 56% | 118.72 | 93.28 | 12 | Jakarta/urban context; local norms vary by agency | 10 | Urban ride-hailing (GoJek/Grab) or local taxi norms
*Estimated - Subject to Approval
** Overseas Per Diem refer to |  | https://icsc.un.org/Home/DailySubsistence
Meeting Package (USD)
City | Average | Lowest | Highest | Notes & Sources
Vientiane | 122.5 | 60 | 185 | Very affordable, with entry-level packages around $60 and luxury setups reaching $180+.
Phnom Penh | 242.5 | 70 | 415 | Wide range—venue-only rates up to $415—expect $100–300 for inclusive full-day
Hanoi | 77.5 | 65 | 90 | Mid-range ~ $70–110; premium intercontinental packages ~$110+.
Manila | 100 | 50 | 150 | Limited public pricing
Bangkok | 55 | 50 | 60 | Typical range ~ $45–75, with premium options slightly higher
Kuala Lumpur | 65 | 50 | 80 | Most meeting packages fall between $70–80 per person full-day.
Jakarta | 70.5 | 46 | 95 | Le Méridien offers a spectrum from half-day engagement to premium full-board options. Gran Mahakam provides slightly lower-priced meeting options. Expect half-day at ~$52, full-day at ~$59 (excluding taxes), and full‑board begins at ~$95 before tax/service
Local Participants Per diem
Country | Per Diem (USD/day) | Lowest |  |  | Basis & Notes
Vietnam | 45 | 35 | 55 |  | Meals + incidentals; lower if meals provided
Cambodia | $35 – $50 | 35 | 50 |  | Often aligned with gov’t or NGO rates
Laos | $35 – $50 | 35 | 50 |  | Consistent with DFAT/UN project norms
Kuala Lumpur | $40 – $65 | 40 | 65 |  | Reflects higher urban cost (meals, transport)
Siem Reap | $35 – $50 | 35 | 50 |  | Similar to Phnom Penh for local participants
Bangkok* | $40 – $65 | 40 | 65 |  | NGOs apply ~30–40% of int’l DSA
Manila* | $40 – $65 | 40 | 65 |  | Urban cost, meals partially included
Indonesia | $35 – $55 | 35 | 55 |  | Jakarta/Bali context; varies by city/partner
Key Assumptions:
These apply to local (national) participants only, not international staff.
Includes lodging, meals, and incidental costs unless otherwise covered.
If meals and venue are provided, a reduced allowance of $10–$15/day is common.
These are not government rates, but typical for NGO/INGO budgeting.
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this per diem to give when having international travel? Not clear to me. Reply: this is estimate for local participants. I need to discuss with Adi as he presented the list to Serene during the last workshop in Jakarta Reply: You can refer the international Per Diem using calculation in UNDSA and the per diem calculator sheet included in Single destination tab and multiple destination tab

## Validation
EXPENDITURE CATEGORY | EXPENDITURE TYPE | Quantity CATEGORY | Unit Currency | Conversion Rate to AUD
Other Direct Costs | Bank Charges | Pax | AUD | 1
Other Direct Costs | Communications | Person | USD | 0.6539
Other Direct Costs | Courier Services | One way | LAK | 14015
Other Direct Costs | Meetings & Conferences | Return | IDR | 10612
Other Direct Costs | Office Expenses | Lumpsum | VND | 17106
Other Direct Costs | Professional Services | Km | MYR | 2.77
Other Direct Costs | Recruitment | Pieces | SGD | 0.836
Other Direct Costs | Translation Services | Unit | NZD | 1.087
Other Direct Costs | Workshops | Event | THB | 21.26
Other Direct Costs | Utilities | Hour | PHP | 39.12
Subcontractors | Subcontractor-External | Day
Travel | Airfare | Monthly
Travel | Accommodation | Annual
Travel | Local Transportation | Semester
Travel | Overseas Per Diem | Quaterly
Travel | Incidental Travel
Travel | Local Per Diem
Travel | Other Allowance